## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-04-g-team7
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
AS A Developer I WANT to submit a request to get the cupboard SO THAT I can update needs in the cupboard. | 1. GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK)
2. GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK)
As a user, I want access to the funding basket so that I can view what items I would like to purchase | **Given** I view the FUNDING BASKET, **when** there is nothing in it **then** it will tell me that no items are there
**GIVEN ** I add a need to the FUNDING BASKET, **WHEN** I logout, **THEN** my information will be saved (persistence) and return status code of 201 (PASS)
**GIVEN ** I add a need to the FUNDING BASKET, **WHEN** I view the funding basket, **THEN** the item will appear
As a user, I want access to the checkout so that I can purchase the items in the funding basket. | GIVEN I hit checkout WHEN there are **needs ** in the checkout THEN the system should clear the checkout, subtract the **needs** in the cart from the **cupboard**, save to the persistent storage, and return status code of 201 (PASS)
GIVEN I checkout WHEN there are **no needs ** in the cart THEN the system should return a status code of 409 (CONFLICT)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.