## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-04-g-team7
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a DEVELOPER I WANT to submit a request to get the cupboard SO THAT I can update needs in the cupboard. | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | ✔ | JK + ZK, 3/20/24 Admin is able to add needs using the input bar; however, the product, id number, and quantities of each item to not show (front-end issue)
| GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | ✔ | JK + ZK, 3/20/24
As a USER I want access to the funding basket so that I can view what items I would like to purchase | GIVEN I view the FUNDING BASKET, WHEN there is nothing in it THEN it will tell me that no items are there | ✔ | JK + ZK, 3/20/24 Currently no funding basket implemented in front-end. |  | ZK, 4/3/24 Funding basket has been fully implemented in front-end.
| GIVEN I add a need to the FUNDING BASKET, WHEN I logout, THEN my information will be saved (persistence) and return status code of 201 (PASS) | ✔ | JK + ZK, 3/20/24 Currently no funding basket implemented in front-end; persistence not yet created. |  | ZK, 4/3/24 Funding basket has been fully implemented in front-end. Persistent storage has been created.
| GIVEN I add a need to the FUNDING BASKET, WHEN I view the funding basket, THEN the item will appear | ✔ | JK + ZK, 3/20/24 Currently no funding basket implemented in front-end; back-end works. |  | ZK, 4/3/24 Funding basket has been fully implemented in front-end.
As a USER I want access to the checkout so that I can purchase the items in the funding basket. | GIVEN I hit checkout WHEN there are needs in the checkout THEN the system should clear the checkout, subtract the **needs** in the cart from the cupboard, save to the persistent storage, and return status code of 201 (PASS) | ✔ | JK + ZK, 3/20/24 Currently no funding basket implemented in front-end; persistence and checkout not yet created. |  | ZK, 4/3/24 Funding basket has been fully implemented in front-end. Persistence and checkout have both been created.
| GIVEN I checkout WHEN there are no needs in the cart THEN the system should return a status code of 409 (CONFLICT) | ✔ | JK + ZK, 3/20/24 Currently no front-end funding basket; checkout not yet created. |  | ZK, 4/3/24 Funding basket has been fully implemented in front-end. Checkout has been created.
As a USER I want to see a list of needs so that I choose what to contribute to. | Given that I am on the site when I am not on the Needs page then I must see a means to navigate to the Needs page | ✔ | JK, 3/20/24
| Given that I am not on the Needs page when I choose the Needs page, then I am taken to the Needs page | ✔ | JK, 3/20/24
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that there are no needs available to contribute | ✔ | JK + ZK, 3/20/24 Message not yet created for empty dashboard.
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and a short description | ✔ | JK + ZK, 3/20/24 Currently no description or text returned when user clicks on need. |  | ZK, 4/3/24 Need text description returned when user clicks on need.
| Given that I am on the Needs page when there are needs in the cupboard, then I see a means to add each need to my funding basket | ✔ | JK, 3/20/24
As a USER, I want to be able to search through needs to add/subtract from my cart so that I can checkout and make a purchase. | GIVEN I add a need object to my cart WHEN I am logged in as a user THEN the system should take the need from the cupboard and add it to my cart, which saves with persistent storage. |  |  | ✔ | ZK, 4/2/24
| GIVEN I add a need to my cart WHEN I am logged in as a user THEN the system should update the cupboard with the correct quantity left. |  |  | ✔ | ZK, 4/3/24 Dashboard quantity only refreshes after exiting need description--need to implement live quantity updates.
| GIVEN I remove a need object from my cart WHEN I am logged in as user THEN the system should take the need from my cart and put it back in the cupboard. |  |  | ✔ | ZK, 4/2/24
| GIVEN I want to edit the catalog, WHEN I am shopping THEN the system should return an error since I do not have access |  |  | ✔ | ZK, 4/2/24
As a USER I want to be able to log out and in so that my information is saved. | GIVEN I want my information to be persistent WHEN I hit login/logout THEN the system should save the information and return a status code of 201 (PASS) |  |  | ✔ | ZK, 4/2/24
| GIVEN I login with my previously used credentials WHEN I access my shopping cart THEN my previously added items should be present with updated quantities & persistent storage. |  |  | ✔ | ZK, 4/2/24
As an Admin I want to add/change/delete needs so that the cupboard can be updated. | GIVEN I edit a need to the cupboard WHEN I am logged in as admin THEN the cupboard should update the need with the correct name, price, and quantity. |  |  | ✔ | ZK, 4/2/24
| GIVEN I add a new need to the cupboard WHEN I am logged in as admin THEN the cupboard should create a new need with the correct name, price, and quantity. |  |  | ✔ | ZK, 4/2/24
| GIVEN I remove a need from the cupboard WHEN I am logged in as admin THEN the need should be removed from the cupboard. |  |  | ✔ | ZK, 4/2/24
| GIVEN a user makes a purchase WHEN I am logged in as admin THEN the U-fund basket should be updated with the correct amount of funds. |  |  |  | ZK, 4/3/24 Profits are currently not kept track of.
| GIVEN a user is shopping WHEN I am logged in as admin THEN their U-fund basket should not be accessible to me. |  |  | ✔ | ZK, 4/2/24
As a USER I want to sort and filter needs so THAT I can view needs as I desire (A-Z, cost, quantity). | GIVEN I sort and filter needs WHEN there are needs in the inventory THEN the system should return the list of needs under the filter and a status code of 201 (PASS) |  |  | ✔ | ZK, 4/2/24
| GIVEN I sort and filter needs WHEN there are no needs in the inventory THEN the system should return a status code of 409 (FAIL) |  |  |  | ZK, 4/3/23 Error message not yet implemented for "NO RESULTS."
| GIVEN I sort and filter needs WHEN I select the sort alphabetically button THEN the system should return the needs in alphabetical order A-Z. |  |  | ✔ | ZK, 4/2/24
| GIVEN I sort and filter needs WHEN I select the sort by cost button THEN the system should return the needs in cost order (ascending/descending). |  |  | ✔ | ZK, 4/2/24
| GIVEN I sort and filter needs WHEN I select the sort by quantity button THEN the system should return the needs in quantity order (ascending/descending). |  |  | ✔ | ZK, 4/2/24
As an ADMIN/USER, I want to toggle the dark mode / light mode buttons SO THAT my eyes don’t strain. | GIVEN there's a dark mode toggle WHEN the toggle is pressed THEN the website theme should switch from light mode to dark mode and vice-versa. |  |  |  | ZK, 4/3/23 All proceeding acceptance criterion have not yet been implemented.
As a USER I want to add coupon codes to my cart so that I receive discounts. | GIVEN I enter a coupon code to my cart WHEN the code is valid THEN a discount should be applied to my cart.
GIVEN I enter a coupon code to my cart WHEN the code is not valid THEN a discount should not be applied to my cart and an error code should be returned (FAIL).
GIVEN I enter a coupon code to my cart WHEN there are no needs in my cart THEN an error message should be returned (FAIL).